## ProjectTeam
Name | GitHub Alias | Short
Sandra Burri | Sandra Burri | burrs3
Silvan Hostettler | hosts1
Moritz Strickler | strim4
Zoran Stajcic | stajz1
Milena Tardo | Aijel | tardm1
Chantal Zbinden | zbinc2
Roberto Tangarife | tange1
Antoni Tomic | tomia1

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | mood barometer & diary | Moody asks Questions and calculates statistics, and if needed gives feedback and recommends measures/advises. Diary collects all user inputs per day. | high | 80h |  |  | work in progress
2 | sleep problems | Moody gives hints and tips for going to sleep | low | 40h
3 | breathing exercise | Moody gives assisted exercises (with visual and acousting support) for calming down | high | 80h
4 | depressions assessment | User answers questionnaire and Moody calculates depression level, and according to severity gives hints and tips | high | 40h
5 | depression history | User sees his personal history of depression level as a simple diagram, different periods of time selectable | medium | 60h
6 | forum | User can interact with other Moody users | low | 200h |  |  | cancelled
7 | physical activity | Moody reminds user of simple physical activities, based on diary trigger (not enough done) | medium | 40h
8 | eating and drinking | Moody reminds user of eating (incl menu advice) and drinking, based on diary trigger (not enough done) | low | 40h
9 | start into the day | Moody sends a push notification on daily basis to cheer up the user in the morning | high | 20h |  |  | work in progress
10 | forgotten medication | User forgets to take medication. Moody reminds him with push notifications about forgotten therapies. | low | 20h
11 | assisted autogenous training | Moody gives assisted exercises for autogenous training. | low | 40h
12 | emergency alerting | In case of emergency, Moody helps the user to alert professional care and also supports him to find the nearest psychatrist | medium | 80h
13 | activity todo list | Moody presents a list of possible activities for today, and the user is able to check done activities | high | 40h |  |  | work in progress

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.16 | 1 | diary elements | Define diary entries | Model, Controller | ??? |  | 2-high |  |  |  | done | siehe 1.4
1.5 | 1 | questions | Define Question type yes/no | Model, Controller | ??? |  | 2-high | 6 |  |  | done | Siehe 1.2
1.0 | 1 | project initialization | Classes, Interfaces, DB Model | Database, Model | strim4 |  | 1-blocker | 2 |  |  | done
0.1 | 1 | design + menu | Design + Menu of Application | UI | zbinc2 |  | 2-high | 6 |  | 6 | done
0.2 | 1 | example layout | Example Layout/View of Application (base view & base presenter) | UI | zbinc2 |  | 1-blocker | 8 |  | 8 | done
0.1 | 1 | design + menu | Design + Menu of Application | UI | tomia1 |  | 2-high | 6 |  |  | done
0.2 | 1 | example layout | Example Layout/View of Application (base view & base presenter) | UI | tomia1 |  | 1-blocker | 8 |  |  | done
1.7 | 1 | UI questions | User interface for questions / answers | UI | burrs3 |  | 2-high | 4 |  | 4 | done
9.3 | 1 | UI | Design User Interface of notification message | UI, Controller | burrs3 |  | 2-high | 4 |  | 4 | done
9.2 | 1 | example messages | Write example notification messages | Database | tardm1 |  | 2-high | 2 |  |  | cancelled
1.15 | 1 | UI diary | User interface for diary | UI | zbinc2 |  | 2-high | 8 |  | 8 | done
1.2 | 1 | Data model | Design data model for questionnaire + questions + answers | Database, Model | hosts1 |  | 2-high | 4 |  | 3 | in progress
1.4 | 1 | Data model | Design data model for diary, diary elements | Database, Model | strim4 |  | 2-high | 6 |  |  | done
9.1 | 1 | Data model | Design data model for notification store | Database, Model | tardm1 |  | 2-high | 6 |  | 1 | done
9.4 | 1 | timer | Define timer for push notification | Controller | stajz1 |  | 2-high | 2 |  | 2 | done
9.5 | 2 | push message | Notification mechanism to push message to operating system | Controller, Model | stajz1 |  | 2-high | 3 |  |  | in progress
9.6 | 1 | mechanism | Mechanism for choosing right message per day | Controller, Model | stajz1 |  | 2-high | 3 |  | 3 | done
1.1 | 1 | Data model | Design data model for profile (including name, contact details) | Database, Model | tange1 |  | 1-blocker | 4 |  | 4 | in progress
13.1 | 2 | Data Model | Datamodel with advice messages | Model | tange1 |  | 2-high | 6 |  | 3 | in progress
13.5 | 2 | UI | Design responsive User Interface for activity list with choice mechanism | UI, Controller | zbinc2 /tarm1 |  | 2-high | 5 |  | 1 | in progress
1.17 | 2 | write recomm. | Write recommendations / Advices | Database | ??? |  | 4-low | 4 |  |  | waiting | Für Sprint 3
1.14 | 2 | UI statistics | User interface for statistics | UI | burrs3 |  | 3-medium | 4 |  |  | waiting
1.18 | 2 | validation context | Define context of validation result with matching recommendation / advices | Model, Controller | burrs3 |  | 4-low | 8 |  |  | waiting
1.6 | 2 | questions | Define Question type emoji | Model, Controller | burrs3 |  | 3-medium | 2 |  |  | waiting
1.10 | 2 | example questions | Write example questions Emoji | Database | burrs3 |  | 4-low | 0.5 |  |  | waiting
1.3 | 1 | Data model | Design data model for validation | Database, Model | hosts1 |  | 2-high | 6 |  |  | waiting
13.2 | 2 | Data Model | Integration of model inside of Database | Model | tange1 |  | 3-medium | 6 |  |  | waiting
13.4 | 2 | Structure of activities | Organisation of activities structure into Categories: season, place and daytime | Model | tange1 |  | 4-low | 6 |  |  | waiting
13.6 | 2 | User input / scalable list | User input is added to the existing list of activities | Model, DB | tange1 |  | 4-low | 5 |  |  | waiting
1.11 | 2 | question validation | Define question validation | Model, Controller | tardm1 |  | 3-medium | 4 |  |  | waiting
1.12 | 2 | questionnaire calculation | Define questionnaire calculation | Model, Controller | tardm1 |  | 3-medium | 4 |  |  | waiting
1.13 | 2 | statistics | Define statistics of questionnaires | Model, Controller | tardm1 |  | 3-medium | 4 |  |  | waiting
1.9 | 2 | example questions | Write questions Yes/no | Database | tardm1 |  | 4-low | 1 |  |  | waiting
13.3 | 2 | Activity List with advice messages | The scalable list of activities | DB, Model | tomia1 |  | 2-high | 6 |  |  | waiting
13.7 | 2 | Persistence / History | The list of done activities is being stored inside of DB | DB, Collections | tomia1 |  | 3-medium | 3 |  |  | waiting
13.8 | 2 | History review | The list of done activities with timestamp is callable over UI | UI, Controller, DB | tomia1 |  | 3-medium | 3 |  |  | waiting
1.8 | 2 | timer questionnaire | Define timer for questionnaire | Model | ??? |  | 3-medium | 4 |  |  | waiting | Für Sprint 3
0.7 | 2 |  | DB persistence (everything else) |  | hosts1 |  | 2-medium | 6
0.8 | 2 |  | UI responsivness |  | hosts1 |  | 2-medium | 8
9.6 | 2 |  | notification store into database |  | stajz1 |  | 2-medium | 4
9.7 | 2 |  | make push notification work |  | stajz1 |  | 1-high | 8
0.9 | 2 |  | diary pictures into database? |  | strim4 |  | 3-medium | 4
0.6 | 2 |  | DB persistence (for diary) |  | strim4 |  | 1-high | 6
0.4 | 2 | class diagram | update class diagram |  | zbinc2 |  | 2-high | 6 |  | 6
0.10 | 2 |  | UI diary connection |  | zbinc2 |  | 2-medium | 4

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 23.11.17 | 72 | 72
1